## Dates
Period End
MA Holiday
No Event
| February | Notes | March | Notes
| 2014-02-03 |  | 2014-03-03 |  | 2014-03-31
| 2014-02-04 |  | 2014-03-04 |  | 2014-04-01
| 2014-02-05 |  | 2014-03-05 |  | 2014-04-02
| 2014-02-06 |  | 2014-03-06 |  | 2014-04-03
| 2014-02-07 |  | 2014-03-07 |  | 2014-04-04
| 2014-02-10 |  | 2014-03-10 |  | 2014-04-07
| 2014-02-11 |  | 2014-03-11 |  | 2014-04-08
| 2014-02-12 |  | 2014-03-12 |  | 2014-04-09
| 2014-02-13 |  | 2014-03-13 |  | 2014-04-10
| 2014-02-14 |  | 2014-03-14 |  | 2014-04-11
| 2014-02-17 | MA Holiday | 2014-03-17 |  | 2014-04-14
| 2014-02-18 |  | 2014-03-18 |  | 2014-04-15
| 2014-02-19 |  | 2014-03-19 |  | 2014-04-16
| 2014-02-20 |  | 2014-03-20 |  | 2014-04-17
| 2014-02-21 |  | 2014-03-21 |  | 2014-04-18
| 2014-02-24 |  | 2014-03-24 |  | 2014-04-21
| 2014-02-25 |  | 2014-03-25 |  | 2014-04-22
| 2014-02-26 |  | 2014-03-26 |  | 2014-04-23
| 2014-02-27 |  | 2014-03-27 |  | 2014-04-24
| 2014-02-28 |  | 2014-03-28 |  | 2014-04-25

## Stakeholders
Hi-light the team column when these goals have been fulfilled
Introductory meeting held
Introductory meeting Arranged
Introductory meeting TBA
Small business area
Out of Scope
| Team | Role | Name | Details | Notes/Business Interests
| Credit Control Manager | Sponsor | [Name of contact] | [Location i.e. 6th floor] [phone number] [email] | [i.e. Collecting money]
| Sales Admin Manager | Project Manager
| SME Dispute Resolutions Credit Control | Key SME
| Other Key Business Areas |  | Contacts Name | Details | Notes/Business Interests
| e.g. Food |  | [Name of contact] | [Location i.e. 6th floor] [phone number] [email] | e.g. Called - issues with Jnl
e.g. Pharmacy
e.g. E-commerce
|  |  |  | No report | Is this in scope?
| Other Stakeholders |  | Names | Details | Notes
e.g. Internal Audit
Internal Audit Report Distribution
| Head of Commercial, Grocery | CJ Antal-Smith
| Trading Finance Manager | Jason Bastow
| Commercial Supplier Communications Manager, Food Retail | Tom Chinnery
| Head of Financial Accounting, Food Retail | Diane Clarke
| Data Integrity and Development Manager | Dave Cooper
| Director of Group Internal Audit | Neil Fletcher
| Finance Manager, Accounts Receivable | Philippa Gayle
| Finance Manager, Invoice Matching, FSSC | Graham Jones
| Head of Commercial, BWST/Frozen | Ian Martin
| Commercial Data Operations Manager | Karen O’Brien
| Head of Commercial - Development and Non-Food | Mark Owen
| Data Management Analyst | Simon Palmer
| Sales Development and Data Manager | Andy Scull
| Seasonal Planning Manager | Emma Smith
| Head of Financial Shared Services Centre | Adam Williams
| EDI Development Team Manager, Food Retail | Yvonne Wilson

## Milestones
Ref | Activity | Date
1 | Workshops/Observations/1-2-1 meetings commenced | 2014-02-01
2 | Full ‘as-is’ Process Documented | 2014-02-28
3 | Timings, Volumes & Outputs documented | 2014-02-28
4 | Analysis of documentation complete | 2014-03-21
5 | Recommendations Workshop held | 2014-03-21
6 | Implementation phase defined and initiated | 2014-03-25

## Milestone RAG
Please note the colour status is a reflection of the progress made against the baseline date. The forecast date can be changed however the colour status should remain a reflection of the original baseline date. If the Steering Group agree to re baseline the milestone the colour status can be updated accordingly.
AR Disputes Process Review Plan |  |  | Project Commentary
Project Status Current Period |  | Y | Findings and next steps workshops have been arranged for 8th, 15th and 17th April. A member of the commercial team has been invited in order to gain consensus with any future projects.As-Is documentation is complete and the finalisation of timings, volumes and dispute values is almost complete. Findings & recommendations will be collated over the next week, thereby being formatted in a presentable document.
Project Status Previous Period |  | Y
Ref | Key Milestones Description | Baseline Date | Forecast Date | Actual Date | Comments | Status
1 | Workshops/Observations/1-2-1 meetings commenced | 2014-02-01 |  | 2014-02-01 |  | B
1.1 | Identify key business areas and contacts to be involved with the review. | 2014-02-01 |  | 2014-02-01 |  | B
1.2 | Sign off TOR | 2014-02-05 |  | 2014-02-11 |  | B
1a | Project Initiated with key business areas | 2014-02-12 |  | 2014-03-07 |  | B
1.1a | Hold mobilisation meeting with key contacts in each business area | 2014-02-12 |  | 2014-03-07 |  | B
2 | Full ‘as-is’ Process Documented | 2014-02-28 |  | 2014-03-27 |  | B
2.1 | Obtain key documentation from AR Credit Control, including procedure manuals and audit reports. | 2014-02-07 |  | 2014-03-07 |  | B
2.2 | Document high level disputes process from a business objective perspective. | 2014-02-07 |  | 2014-02-07 |  | B
2.3 | Identify key process areas within the key business areas to be reviewed. | 2014-02-14 |  | 2014-02-24 |  | B
2.4 | Document high level disputes process from FSSC perspective. | 2014-02-14 |  | 2014-02-28 |  | B
2.5 | Obtain key documentation from other business areas, including procedure manuals and audit reports. | 2014-02-21 |  | 2014-02-28 |  | B
2.6 | Identify audit and risk concerns that are currently being addressed within the processes as well as any gaps that might currently exist. | 2014-02-21 |  | 2014-02-24 |  | B
2.7 | Document individual 'as-is' disputes processes in the form of Swim Lanes for FSSC as well as key business areas. | 2014-02-28 |  | 2014-03-07 |  | B
2.8 | Identify and map key 'as-is' processes in a consolidated format between the key business areas | 2014-02-28 |  | 2014-03-27 | Individual processes are mapped and work has begun to map out a consolidated | B
3 | Timings, Volumes & Outputs documented | 2014-03-07 | 2014-03-28 |  |  | Y
3.1 | Obtain key reporting information as distributed to the business by AR Credit Control | 2014-02-07 |  | 2014-02-14 | All dispute reports for in-scope business areas have now been received | B
3.2 | Obtain timing and volume information regarding invoice dispute queries both within FSSC and across the business | 2014-02-14 |  | 2014-03-07 |  | B
3.3 | Obtain disputes reporting information as distributed used by the business to assist with dispute resolution | 2014-02-21 |  | 2014-03-21 |  | B
3.4 | Map out details dispute resolution timings and volumes for both man hours and lead time | 2014-02-28 | 2014-03-28 |  |  | Y
4 | Compile research and analyse data in greater detail | 2014-03-21 |  |  |  | Y
4.1 | Produce a list of findings from the various processes | 2014-03-07 | 2014-04-02 |  |  | Y
4.2 | Identify recurrent themes/issues as well as bottlenecks across processes | 2014-03-07 |  | 2014-03-07 |  | B
4.3 | Investigate issues further to gain understanding of background and any suggestions/plans for mitigation | 2014-03-14 | 2014-04-02 |  |  | Y
4.4 | Identify possible quantifiable benefits relating to lead time and process time that changes could achieve | 2014-03-19 | 2014-04-02 |  |  | Y
4.5 | Produce list of recommendations for process improvement and categorise into quick wins/long term changes etc | 2014-03-21 | 2014-04-02 |  |  | Y
5 | Recommendations Workshop held | 2014-03-21 |  |  | Slightly delayed due to resource availability within FS&C | Y
5.1 | Identify required attendees and book the workshops | 2014-02-28 |  | 2014-03-14 | To be agreedwith sponsors in update meeting on 14/03/14 | B
5.2 | Outline workshop format produce compile supporting documentation | 2014-03-07 |  | 2014-03-20 |  | B
5.2a | Compile supporting documentation for workshop purposes | 2014-03-20 | 2014-04-02 |  |  | Y
5.3 | Present findings to key stakeholders and obtain feedback on findings and recommendations | 2014-03-21 | 2014-04-17 |  |  | Y
6 | Implementation phase defined and initiated | 2014-03-25 | 2014-04-24 |  |  | Y
6.1 | Obtain business agreement on implementation initiatives to take forward | 2014-03-25 | 2014-04-24 |  |  | Y
6.2 | create phase 2 TOR/Project Charter for agreed initiatives | 2014-03-25 | 2014-04-24 |  |  | Y
Note on I7: Group IS: Please note the colour status is a reflection of the progress made against the baseline date. The forecast date can be changed however the colour status should remain a reflection of the original baseline date. If the Steering Group agree to re baseline the milestone the colour status can be updated accordingly.

## MA Actions
Actions to be completed by Matt Adams
No. | DATE ACTION LOGGED | ACTION | BY WHEN | Status | KEY DECISIONS / Follow-up actions | RAG
Ring Carol Arnot - Primary Logistics
|  | Contact Buyers (hold VOE) - Matthew Layland, Richard Dennet |  |  | Emailed Matthew Leyland/M Schofield
Hold VOE with CRTG Returns (Central Income / Bonus Income)
Hold VOE with CRTG Admin